Green Pledge

Action Plan Template

| Pledge Commitment | Actions Required | Responsible Person | Deadline | Resources Required |
| --- | --- | --- | --- | --- |

EXAMPLE OF COMPLETED ACTION PLAN

Example Green Pledge

Real Estate Solutions pledges to:

- Energy – Reduce total energy use by 15% by the end of 2024

- Water –  Reduce total water use by 15% by the end of 2024

- Waste – Implement a recycling system for plastic, glass and aluminum within 2 months

- Responsible Purchasing – Eliminate purchasing of single-use plastics by the end of 2024

- Eco-friendly Development / Operations – Ensure new hotel suites in our real estate portfolio are appropriately setback from the beachfront to prevent beach erosion and ensure resilience to sea level rise

- Eco-Action – Ensure all staff volunteer for at least two environmental service projects in 2024.

- Eco-Education – Sponsor an environmental education initiative or activity for at least one primary school class in 2024

- Advocacy – Advocate for the passage of the Environment and Climate Change Bill before the end of 2024

Example Action Plan

The example completed Action Plan Template below is based on the example Green Pledge above for a typical office-based business. This example is provided for guidance only. Please note that figures included are fictitious for illustrative purposes only.

| Pledge Commitment | Actions Required | Responsible Person | Deadline | Resources Required* |
| --- | --- | --- | --- | --- |
| Energy Reduce total energy use by 15% by the end of 2024 | - Replace all light bulbs in the office with LED bulbs - Create and share a company energy policy requiring all staff to: - Turn off computers at the end of each business day and set computers to hibernate after 30 minutes of inactivity - Turn off air conditioning units at the end of each day - Keep air conditioning at the recommended indoor comfort temperature of 78 degrees Fahrenheit - Update company procurement rules to ensure all new devices purchased are energy efficient | Office Manager Human Resources Manager Finance Manager | Within 1 month of Pledge Within 2 weeks of Pledge Within 2 weeks of Pledge | $100 IT to send automated reminders to staff close to the end of each day 5% increase in procurement budget (cost recovered in energy savings) |
| Water Reduce total water use by 15% by the end of 2024 | - Upgrade all faucets to low flow faucets that use a maximum of 1.5 gallons per minute - Upgrade all toilets to low flush toilets that use a maximum of 1.6 gallons per flush - Fix all leaky toilets and faucets | Office Manager Office Manager Office Manager | Within 3 months of Pledge Within 3 months of Pledge Within 2 weeks of Pledge | $600 $1,200 $100 |
| Waste Implement a recycling system for plastic, glass and aluminum within 2 months | - Set up a 3-compartment recycling bin station in the office kitchen - Designate staff to dispose of recyclables at the We Recycle Center at Paraquita Bay, Tortola or The Valley, Virgin Gorda. Please call 443-1775 for instructions and directions. *For guidance in setting up recycling stations and collection options through Green VI, please contact 346-4040. | Office Manager Office Manager | Within 1 month of Pledge Within 1 month of Pledge | $100 N/A |
| Responsible Purchasing Eliminate purchasing of single-use plastics by the end of 2024 | - Purchase a 5-gallon water cooler for the office - Contract supply of water and cleaning of cooler | Office Manager Office Manager | Within 1 month of Pledge Within 1 month of Pledge | $250 $100/month |
| Eco-friendly Development / Practices Ensure new hotel suites in our real estate portfolio are appropriately setback from the beachfront to prevent beach erosion and ensure resilience to sea level rise | - Develop a company policy for new development requiring: - Consulting with the Ministry of Environment, Natural Resources and Climate Change at the beginning of conceptual development planning to ensure plans are best fit for the surrounding environment - Hiring an environmental expert to ensure the environment is best factored throughout development planning and recommended environmental mitigation measures are strictly adhered to during development | General Manager | Within 2 months of Pledge | N/A |
| Eco-Action Ensure all staff volunteer for at least two environmental service projects in 2024. | - Organise a mangrove clean up activity for International Coastal Cleanup Day - Write to all environmental NGOs offering a staff volunteer day in 2024 | Human Resources Manager Human Resources Manager | September 21, 2024 Within 2 weeks of Pledge | $150 N/A |
| Eco-Education Sponsor an environmental education initiative or activity for at least one primary school class in 2024. | - Reach out to a local environmental agency or NGO to sponsor a school education programme | Finance Manager | Within 2 weeks of Pledge | $500 |
| Advocacy Advocate for the passage of the Environment and Climate Change Bill before the end of 2024 | - Write a letter of support to the Ministry of Environment, Natural Resources and Climate Change - Write a letter of support to the editors of local newspapers | General Manager General Manager | Within 1 month of Pledge Within 1 month of Pledge | N/A N/A |